## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-11-b banana
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | LG, 10/14/2018
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | LG, 10/14/2018
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | LG, 10/14/2018
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | LG, 10/14/2018
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | LG, 10/14/2018
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | LG, 10/14/2018
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Fail | LG, 10/14/2018, The sign-out functionality is not present in the SignIn user story. To be implemented in SignOut story.
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | LG, 10/14/2018
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | LG, 10/14/2018
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MB, 10/14/2018
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MB, 10/14/2018
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MB, 10/14/2018
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MB, 10/14/2018
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MB, 10/14/2018
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MB, 10/14/2018
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MB, 10/14/2018
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MB, 10/14/2018
As a Player I want to sign-out so that I don't appear in the lobby as ready to play. | Given I am logged in already when I click the sign out button, then I expect to return to the home page being logged out.
Given that I am not logged in, when I am on the homepage, then I expect not to see a sign out button.
As a player, I want to be able to do simple diagonal moves into valid spaces so that I can follow the rules of checkers. | Given a piece has a valid space to move when I move the piece then I expect the piece to move to a valid space.
Given a piece that has no valid spaces to move, when I attempt to move the piece then I expect the piece to stay in its current space.
Given it is not my turn when I try to move a piece then I expect the piece to stay in its current place
As a Player I want to be forced to capture an opponent’s piece by jumping over it if possible, diagonally, to an adjacent vacant square so that my opponent loses a piece. | Given that at least one of my pieces are in position to make a valid jump of an opponents piece, when it is my turn then I expect to only be able to make a valid jump move.
Given that I am not in position to make a valid jump move, when I try to make a jump move, then I expect the game to reject it.
Given it is not my turn when I try to move a piece then I expect the piece to stay in its current place weather or not the move is valid.
Given that a valid jump move to be made when I jump the other players piece then I expect the jumped pice to be eliminated.
As a Player I want to be able to capture several of an opponent’s pieces so that my opponent loses pieces. | Given I have jumped a player when there are more valid sequential jumps then the player jumps all valid pieces.
Given I have jumped a piece when there are no valid sequential jumps then the piece cannot be moved.
Given it is not my turn when I try to move a piece then I expect the piece to stay in its current place weather or not the move is valid.
Given that a valid multi-jump move can be made when I jump the other players pieces then I expect the jumped pieces to be eliminated.
As a player, when all of a player’s pieces are eliminated, I want a victory to be given to the opposing player so that they win. | Given that I have a valid move to eliminate my opponent when I jump the final piece of my opponent's then I win the game.
Given that I only have one piece left, when my piece gets eliminated then I lose the game.
As a player, I want the game to end when a player forfeits so that a victory is given to the other player. | Given that I am in a game when I click the forfeit button then it automatically loses me the game and sends me back to the lobby. |  |  | Pass | MK, 11/5/2018
| Given that I am in a game when my opponent forfeits then the game automatically wins me the game and sends me a message notifying me about my opponent resigning. |  |  | Pass | MK, 11/5/2018, Comments: If it is the player's turn and the opponent resigns while it is not their turn, the message only displays after the player submits their turn and there are some exceptions being raised.
| Given that I was in a game when I am at the home page and want to start another game, then I am able to start a new game. |  |  | Pass | MK, 11/5/2018